Sprint 0 – 25th April – 04th May
Id	Description	Owner	Importance	Estimate (hours)	Date start	Date end	Real time	Cost (hours)	Status
1	Title, purposes	Sergio	Low	1	25/04/14	25/04/14	1		DONE
2	Functional and non-functional requirements	Sergio	High	2	25/04/14	25/04/14	2		DONE
3	Use case diagram and their textual description,	Sergio	High	6	25/04/14	26/04/14	7		DONE
4	Entity-relation diagram	Sergio	High	3	27/04/14	27/04/14	3		DONE
5	description of the methodology used and project planning (Agile or classic approaching with Gantt: dates, tasks and resources with their costs).	Sergio	Low	2	03/05/14	03/05/14	3		DONE
6	Test Cases	Sergio	High	3	04/05/14	04/05/14	3		DONE
7	Classes Diagram	Sergio	High	2	05/05/14	05/05/14	1		DONE

Sprint 5 – 9th May
Id	Description	Owner	Importance	Estimate (hours)	Date start	Date end	Real time	Cost (hours)	Status

7	Add sounds to register page and key capture	Sergio	High	4	05/04/14	05/04/14	9		DONE
	Create inteface of login page
	Create functionality of login page (JS)
	Create functionality of login page (PHP)
	Add sounds to register page and key capture
	Add sounds to register page and key capture
	Create inteface of home page of student
	Add sounds to home page of student and key capture
	Create interface of game introduction
	Create functionality of game introduction page
	Add sounds to game introduction page and key capture
	Create interface of the game
	Create functionality of game
	Add sounds to game and key capture
	Create interface of the end game
	Create functionality of end game (JS)
	Create functionality of end game (PHP)
	Add sounds to end game page and key capture
	Create functionality of logout
	Add sounds to logout

Sprint 5 – 9th May
Id	Description	Owner	Importance	Estimate (hours)	Date start	Date end	Real time	Cost (hours)	Status
1	Create SQL	Sergio	High	1	05/05/14	05/05/14	1		DONE
2	Create interface of home page	Sergio	Low	1	05/05/14	05/05/14	1		DONE
3	Add sounds to home page and key capture	Sergio	High	1	05/05/14	05/05/14	2		DONE
4	Create inteface of register page	Sergio	Low	3	05/05/14	06/05/14	4		DONE
5	Create functionality of register page (JS)	Sergio	High	5	06/05/14	08/05/14	5		DONE
6	Create functionality of register page (PHP)	Sergio	High	4	08/05/14	09/05/14	4		DONE

Sprint 12 – 16th May
Id	Description	Owner	Importance	Estimate (hours)	Date start	Date end	Real time	Cost (hours)	Status
1	Add sounds to register page and key capture	Sergio	High	6	12/05/14	14/05/14	10		DONE
2	Create inteface of login page	Sergio	High	1	15/05/14	15/04/14			DONE
3	Create functionality of login page (JS)	Sergio	High	2	15/04/14	15/04/14	3		DONE
4	Create functionality of login page (PHP)	Sergio	High	2	16/04/14	16/04/14	2		DONE

Sprint 19 – 23th April – 04th May
Id	Description	Owner	Importance	Estimate (hours)	Date start	Date end	Real time	Cost (hours)	Status
1	Add sounds to login page and key capture	Sergio	High	3	19/05/14	19/05/14	3		DONE
3	Create inteface of home page of student	Sergio	Low	2	19/05/14	19/05/14	2		DONE
4	Add sounds to home page of student and key capture	Sergio	High	4	19/05/14	20/05/14	4		DONE