Sprint 0 – 25th April – 04th May
Id	Description	Owner	Importance	Estimate (hours)	Date start	Date end	Real time	Cost (hours)	Status
1	Title, purposes	Sergio	Low	1	25/04/14	25/04/14	1		DONE
2	Functional and non-functional requirements	Sergio	High	2	25/04/14	25/04/14	2		DONE
3	Use case diagram and their textual description,	Sergio	High	6	25/04/14	26/04/14	7		DONE
4	Entity-relation diagram	Sergio	High	3	27/04/14	27/04/14	3		DONE
5	description of the methodology used and project planning (Agile or classic approaching with Gantt: dates, tasks and resources with their costs).	Sergio	Low	2	03/05/14	03/05/14	3		DONE
6	Test Cases	Sergio	High	3	04/05/14	04/05/14	3		DONE
7	Classes Diagram	Sergio	High	2	05/05/14	05/05/14	1		DONE

Sprint 5 – 9th May
Id	Description	Owner	Importance	Estimate (hours)	Date start	Date end	Real time	Cost (hours)	Status
1	Create SQL	Sergio	High	1	05/05/14	05/05/14	1		DONE
2	Create interface of home page	Sergio	Low	1	05/05/14	05/05/14	1		DONE
3	Add sounds to home page and key capture	Sergio	High	1	05/05/14	05/05/14	2		DONE
4	Create inteface of register page	Sergio	Low	3	05/05/14	06/05/14	4		DONE
5	Create functionality of register page (JS)	Sergio	High	5	06/05/14	08/05/14	5		DONE
6	Create functionality of register page (PHP)	Sergio	High	4	08/05/14	09/05/14	4		DONE

Sprint 12 – 16th May
Id	Description	Owner	Importance	Estimate (hours)	Date start	Date end	Real time	Cost (hours)	Status
1	Add sounds to register page and key capture	Sergio	High	6	12/05/14	14/05/14	10		DONE
2	Create inteface of login page	Sergio	High	1	15/05/14	15/04/14			DONE
3	Create functionality of login page (JS)	Sergio	High	2	15/04/14	15/04/14	3		DONE
4	Create functionality of login page (PHP)	Sergio	High	2	16/04/14	16/04/14	2		DONE

Sprint 19 – 23th May – 04th May
Id	Description	Owner	Importance	Estimate (hours)	Date start	Date end	Real time	Cost (hours)	Status
1	Add sounds to login page and key capture	Sergio	High	3	19/05/14	19/05/14	3		DONE
3	Create inteface of home page of student	Sergio	Low	2	19/05/14	19/05/14	2		DONE
4	Add sounds to home page of student and key capture	Sergio	High	4	19/05/14	20/05/14	4		DONE
5	Create interface of game introduction	Sergio	Low	1	20/05/14	20/05/14	1		DONE
6	Create functionality of game introduction page	Sergio	Medium	2	20/05/14	20/05/14	3		DONE
7	Add sounds to game introduction page and key capture	Sergio	High	3	21/05/14	23/05/14	5		DONE

Sprint 26 – 30th May – 04th May
Id	Description	Owner	Importance	Estimate (hours)	Date start	Date end	Real time	Cost (hours)	Status
1	Create interface of the game	Sergio	Low	1	26/05/14	26/05/14	2		DONE
2	Create functionality of game	Sergio	High	4	26/05/14	26/05/14	9		DONE
3	Add sounds to game and key capture	Sergio	High	4	27/05/14	27/05/14	6		DONE
4	Create interface of the end game	Sergio	Low	1	28/05/14	28/05/14	1		DONE
5	Create functionality of end game (JS)	Sergio	High	3	28/05/14	28/05/14	3		DONE
6	Create functionality of end game (PHP)	Sergio	High	2	29/05/14	29/05/14	2		DONE
7	Add sounds to end game page and key capture	Sergio	High	3	29/05/14	30/05/14	5		DONE

Sprint 02 – 06th April – 04th May
Id	Description	Owner	Importance	Estimate (hours)	Date start	Date end	Real time	Cost (hours)	Status
1	Create functionality of logout	Sergio	Low	5	02/06/14	03/06/14	6		DONE
2	Add sounds to logout	Sergio	High	2	04/06/14	04/06/14	3		DONE